## Bug Fixes
Task | Priority | Who | Which files are touched
If you leave user and password blank and click the login button it creates a user. | A | Ana Gorohovschi | MarchMadnessGUI.java SerializeTest.java
Trouble finalizing. Is it related to Villanova? | A | Martin&Daniel
Clicking the clear button potentially allow a team to both be eliminated and win. a. Clicking clear while in a region does not clear the final teams. | A
Error when finalizing “null.ser(access denied)”. | B
Clear button in FULL region clears only the EAST division. | B
Once the simulation has been completed, user can’t log out? | B
The user can change a finalize bracket (user can cheat!). | B
The system allows the user to create unlimited users. | C

## Features
Task | Priority | Who | Which files are touched
Add password encryption. | A
Remove user accounts. | B | Joseph | MarchMadnessGUI
Add color. | B | Alex | BracketPane, MarchMadnessGUI
Resize the full bracket without side scrolling. | B | Thien | MarchMadnessGUI
Add seed numbers to brackets. | C

## Improvements
Task | Priority | Who | Which files are touched
Add minimum password length. | A | Nikolas | MarchMadnessGUI
Clarify the clear and reset button. | A
Have a create user button on the login page. | A
Redesign the class UML. | A
Implement the simple tutorial. This can be helpful for checking the teams states | A | Devin/Paul | MarchMadnessGUI
Add a warning confirmation dialog when the user is about to finalize. | B
Resize (Northern Kentucky, South Dakota State) | C
Can’t logout until finalize button is clicked. | C
Change orientation of choose division buttons. | C
Final two teams should be on top of the platform. | C
Place buttons in one area (drop dpwn menu for the users instead of button) | C
Welcome message on startup | C
“user winning teams” selection for the simulation board | C